## Sheet1
Major Task
Complete Android GUI(20) | Complete MiniMax Algorithm(20) | Complete A* Algorithm(20) | Connecting Everything (10) | Extra(5)
Sub Task
Reseach over topic | Reseach over topic | Reseach over topic | Research how to do this | Design Doc | Projected Rate | Acutual | Task
Complete Game board activity | Design utility function | design heuristic | Install NDK | Post Prod. Notes | 75 | 75 | 0
Complete Menu activity | Code apropriate node | implement A* algorithm | Connect A* to GUI | Test Log | 68.75 | 74 | 0
implement Difficulty placements | Implement Mini - Max Tree | debugg | Connect MiniMax to GUI | Presentation | 62.5 | 70 | 1
| Implement Alpha beta |  | debugg and Complete |  | 56.25 | 68 | 0
| debugg |  |  |  | 50 | 60 | 2
[5 empty] | 43.75 | 53 | 2
[5 empty] | 37.5 | 39 | 7
[5 empty] | 31.25 | 36 | 0
[5 empty] | 25 | 29 | 1
[5 empty] | 18.75 | 29 | 0
[5 empty] | 12.5 | 10 | 9
[5 empty] | 6.25 | 5 | 2
[5 empty] | 0 | 0 | 2